{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["List1","List2","List3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"List1","index":0,"n_rows":67,"n_cols":137,"rows_kept":67,"cut":false,"hidden":false,"merged":[[5,10,5,16],[5,17,5,23],[5,24,5,30],[5,31,5,37],[5,38,5,44],[1,2,3,142],[47,2,49,142],[50,121,50,142],[51,87,51,93],[51,94,51,100],[51,101,51,107],[51,108,51,114],[51,115,51,121],[51,122,51,128],[51,129,51,135],[51,136,51,142],[4,2,6,2],[50,2,52,2],[4,3,4,27],[4,28,4,55],[5,3,5,9],[5,45,5,51],[6,108,6,114],[6,87,6,93],[6,94,6,100],[6,101,6,107],[6,38,6,44],[6,45,6,51],[6,52,6,58],[6,59,6,65],[6,66,6,72],[51,38,51,44],[51,45,51,51],[51,52,51,58],[51,59,51,65],[51,66,51,72],[50,3,50,28],[50,29,50,58],[6,73,6,79],[6,80,6,86],[51,3,51,9],[51,10,51,16],[51,17,51,23],[51,24,51,30],[6,3,6,9],[6,10,6,16],[6,17,6,23],[6,24,6,30],[6,31,6,37],[51,73,51,79],[51,80,51,86],[51,31,51,37],[52,122,52,128],[52,129,52,135],[52,136,52,142],[52,3,52,9],[52,10,52,16],[52,17,52,23],[52,24,52,30],[52,31,52,37],[52,38,52,44],[52,45,52,51],[52,52,52,58],[52,59,52,65],[52,66,52,72],[52,73,52,79],[52,80,52,86],[6,122,6,128],[6,129,6,135],[6,136,6,142],[5,80,5,86],[4,56,4,86],[5,108,5,114],[4,87,4,116],[4,117,4,142],[5,52,5,58],[5,59,5,65],[5,66,5,72],[5,73,5,79],[5,115,5,121],[5,122,5,128],[5,129,5,135],[5,136,5,142],[5,87,5,93],[5,94,5,100],[5,101,5,107],[52,108,52,114],[50,90,50,120],[52,87,52,93],[50,59,50,89],[52,94,52,100],[52,101,52,107],[52,115,52,121],[6,115,6,121]]}
[]
[null,null,"Harmonogram prací - ČOV            Škvořetice  "]
[]
[]
[null,null,"rok 2019","leden",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"únor",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"březen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"duben",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"květen"]
[null,null,null,"2.týd",null,null,null,null,null,null,"3.týd.",null,null,null,null,null,null,"4.týd",null,null,null,null,null,null,"5.týd",null,null,null,null,null,null,"6.týd",null,null,null,null,null,null,"7.týd",null,null,null,null,null,null,"8.týd",null,null,null,null,null,null,"9.týd",null,null,null,null,null,null,"10.týd",null,null,null,null,null,null,"11.týd",null,null,null,null,null,null,"12.týd",null,null,null,null,null,null,"13.týd",null,null,null,null,null,null,"14.týd",null,null,null,null,null,null,"15.týd",null,null,null,null,null,null,"16.týd.",null,null,null,null,null,null,"17.týd.",null,null,null,null,null,null,"18.týd.",null,null,null,null,null,null,"19.týd",null,null,null,null,null,null,"20.týd.",null,null,null,null,null,null,"21.týd."]
[null,null,null,"13.1.",null,null,null,null,null,null,"20.1.",null,null,null,null,null,null,"27.1.",null,null,null,null,null,null,"3.2.",null,null,null,null,null,null,"10.2.",null,null,null,null,null,null,"17.2.",null,null,null,null,null,null,"24.2.",null,null,null,null,null,null,"3.3.",null,null,null,null,null,null,"10.3.",null,null,null,null,null,null,"17.3.",null,null,null,null,null,null,"24.3.",null,null,null,null,null,null,"31.3.",null,null,null,null,null,null,"7.4.",null,null,null,null,null,null,"14.4.",null,null,null,null,null,null,"21.4.",null,null,null,null,null,null,"28.4.",null,null,null,null,null,null,"5.5.",null,null,null,null,null,null,"12.5.",null,null,null,null,null,null,"19.5.",null,null,null,null,null,null,"26.5."]
[null,null,"SO 01.1 Provozní objekt s aktivací žb.část"]
[null,null,"zemní práce (denitrifikace,nitrifikace,dosazovací nádrž,kalojem)"]
[null,null,"čerpací jímky,drenáž"]
[null,null,"podkladní vrstvy zkameniva 63-125, 0-32"]
[null,null,"podkladní beton tl.100 mm"]
[null,null,"izolace"]
[null,null,"bednění"]
[null,null,"výztuž základové desky D1"]
[null,null,"betonáž základové desky D1"]
[null,null,"technologická přestávka 2 dny"]
[null,null,"demontáž bednění desky D1"]
[null,null,"montáž bednění stěn 1/2"]
[null,null,"montáž výztuže stěn"]
[null,null,"montáž bednění stěn 2/2"]
[null,null,"betonáž stěn"]
[null,null,"technologická přestávka 7 dní"]
[null,null,"demontáž bednění stěn"]
[null,null,"zkouška vodotěsnosti denitrifikace+dosazovací nádrž"]
[null,null,"zkouška vodotěsnosti kalojem+nitrifikace"]
[null,null,"zpětný zásyp žb,části ČOV"]
[null,null,"provozní objekt s aktivací"]
[null,null,"podkladní beton tl 50mm"]
[null,null,"montáž výztuže včetně bednění"]
[null,null,"betonáž desky"]
[null,null,"základy+ZTI"]
[null,null,"česle komplet"]
[null,null,"zpětný zásyp,příprava pod podlahu"]
[null,null,"podkladní beton+hrubá podlaha"]
[null,null,"hrubá stavba"]
[null,null,"SO 01.4 Propojovací potrubí"]
[null,null,"odtok DN 250,výústní objekt-měrná šachta,D=66,5 bm"]
[null,null,"zemní práce VO+příprava pro odláždění koryta potoka"]
[null,null,"kompletní realizace výustního objektu"]
[null,null,"zpevnění koryta potoka"]
[null,null,"obtok ČOV"]
[null,null,"SO 01.4 Zpevněné plochy,oplocení,terenní úpravy"]
[null,null,"příprava území"]
[null,null,"zemní práce-staveništní komunikace"]
[null,null,"drenáž"]
[null,null,"kcční vrstvy"]
[null,null,"Harmonogram prací - ČOV            Škvořetice  "]
[]
[]
[null,null,"rok 2019","květen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"červen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"červenec",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"srpen",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"září"]
[null,null,null,"19.týd",null,null,null,null,null,null,"20.týd.",null,null,null,null,null,null,"21.týd",null,null,null,null,null,null,"22.týd",null,null,null,null,null,null,"23.týd",null,null,null,null,null,null,"24.týd",null,null,null,null,null,null,"25.týd",null,null,null,null,null,null,"26.týd",null,null,null,null,null,null,"27.týd",null,null,null,null,null,null,"28.týd",null,null,null,null,null,null,"29.týd",null,null,null,null,null,null,"30.týd",null,null,null,null,null,null,"31.týd",null,null,null,null,null,null,"32.týd",null,null,null,null,null,null,"33.týd.",null,null,null,null,null,null,"34.týd.",null,null,null,null,null,null,"35.týd.",null,null,null,null,null,null,"36.týd.",null,null,null,null,null,null,"37.týd.",null,null,null,null,null,null,"38.týd."]
[null,null,null,"12.5.",null,null,null,null,null,null,"19.5.",null,null,null,null,null,null,"26.5.",null,null,null,null,null,null,"2.6.",null,null,null,null,null,null,"9.6.",null,null,null,null,null,null,"16.6.",null,null,null,null,null,null,"23.6.",null,null,null,null,null,null,"30.6.",null,null,null,null,null,null,"7.7.",null,null,null,null,null,null,"14.7.",null,null,null,null,null,null,"21.7.",null,null,null,null,null,null,"28.7.",null,null,null,null,null,null,"4.8.",null,null,null,null,null,null,"11.8.",null,null,null,null,null,null,"18.8.",null,null,null,null,null,null,"25.8.",null,null,null,null,null,null,"1.9.",null,null,null,null,null,null,"8.9.",null,null,null,null,null,null,"15.9.",null,null,null,null,null,null,"22.9."]
[null,null,"provozní objekt s aktivací"]
[null,null,"hrubá stavba"]
[null,null,"konstrukce truhlářské"]
[null,null,"konstrukce pokrývačské"]
[null,null,"vnitřní omitky,elektroinstalace,obklady"]
[null,null,"konstrukce zámečnické"]
[null,null,"SO PS ČOV provozní soubory"]
[null,null,"strojní část ČOV (ENVI-PUR)"]
[null,null,"elektroinstalace ČOV (ENVI-PUR)"]
[null,null,"SO 01.4 Zpevněné plochy,oplocení,ter.úpravy"]
[null,null,"komunikace"]
[null,null,"oplocení"]
[null,null,"ter.úpravy"]
[null,null,"zahájení zkušebního provozu"]

{"sheet":"List2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"List3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}